## Team Members
Team Member | Contact Phone | Normal Hours | Normal Workdays
Zach Burmeister | 8138628846
Cam Hager | 6518956609
Paul Sanchez | 7196715291
Julia Tremaroli | 7193230319

## Data Warehouse
Data Warehouse Objects Worksheet
Object Name | Description | Source | Source Type | Destination Type
DWBroadcloth | Data Warehouse | Broadcloth OLTP | Database | Database
DWBroadcloth.dbo.FactProduction | Fact Table | Broadcloth.dbo.ProductionBatch | Table | Table
DWBroadcloth.dbo.DimProductionBatch.FactoryID | Dimension Key Column | Broadcloth.dbo.ProductionBatch.FactoryID | int | int
DWBroadcloth.dbo.DimProductionBatch.ItemID | Dimension Key Column | Broadcloth.dbo.ProductionBatch.ItemID | int | int
DWBroadcloth.dbo.DimProductionBatch.StartDateTime | Dimension Key Column | Broadcloth.dbo.ProductionBatch.StartDateTime | datetime | int
DWBroadcloth.dbo.DimProductionBatch.QuantityProduced | Dimension Column | Broadcloth.dbo.ProductionBatch.QuantityProduced | int | int
DWBroadcloth.dbo.DimProductionBatch.EstEndTime | Dimension Column | Broadcloth.dbo.ProductionBatch.EstEndTime | datetime | int
DWBroadcloth.dbo.DimProductionBatch.ActualEndTime | Dimension Column | Broadcloth.dbo.ProductionBatch.ActualEndTime | datetime | int
DWBroadcloth.dbo.DimProductionBatch.ProductionCost | Dimension Column | Broadcloth.dbo.ProductionBatch.ProductionCost | numeric(38,4) | numeric(38,4)
DWBroadcloth.dbo.DimProductionBatch.CostCurrency | Dimension Column | Broadcloth.dbo.ProductionBatch.CostCurrency | nvarchar(5) | nvarchar(5)
DWBroadcloth.dbo.DimProductionBatch.CostExchangeRate | Dimension Column | Broadcloth.dbo.ProductionBatch.CostExchangeDate | datetime | int
DWBroadcloth.dbo.DimProductionBatch.OrderID | Dimension Key Column | Broadcloth.dbo.ProductionBatch.OrderID | int | int
DWBroadcloth.dbo.DimProductionBatch.QualityRating | Measure Column | Broadcloth.dbo.ProductionBatch.QualityRating | numeric(18,0) | numeric(18,0)
DWBroadcloth.dbo.Shipment | Dimesion Table | Broadcloth.dbo.Shipment | Table | Table
DWBroadcloth.dbo.DimShipments.ShipmentID | Dimension Key Column | Broadcloth.dbo.Shipments.ShipmentID | na | int
DWBroadcloth.dbo.DimShipments.ShipMethod | Dimension Column | Broadcloth.dbo.Shipments.ShipMethod | nvarchar(50) | nvarchar(50)
DWBroadcloth.dbo.DimShipments.ShipDate | Dimension Column | Broadcloth.dbo.Shipments.Shipdate | datetime | int
DWBroadcloth.dbo.DimShipments.ShipPostal | Dimension Column | Broadcloth.dbo.Shipments.ShipPostal | nvarchar(12) | nvarchar(12)
DWBroadcloth.dbo.DimShipments.ShipState | Dimension Column | Broadcloth.dbo.Shipments.ShipState | nvarchar(20) | nvarchar(20)
DWBroadcloth.dbo.DimShipments.ShipNation | Dimension Column | Broadcloth.dbo.Shipments.ShipNation | nvarchar(50) | nvarchar(50)
DWBroadcloth.dbo.DimShipments.ShipCurrency | Dimension Column | Broadcloth.dbo.Shipments.ShipCurrency | nvarchar(5) | nvarchar(5)
DWBroadcloth.dbo.DimShipmentItem.QuantityShipped | Dimension Column | Broadcloth.dbo.ShipmentItem.QuantityShipped | int | int
DWBroadcloth.dbo.Compliance | Dimesion Table | Broadcloth.dbo.Compliance | Table | Table
DWBroadcloth.dbo.DimCompliance.ComplianceID | Dimension Key Column | Generated | na | int
DWBroadcloth.dbo.DimCompliance.DateObserved | Dimension Column | Broadcloth .dbo.Compliance.DateObserved | datetime | int
DWBroadcloth.dbo.DimCompliance.OverallRating | Dimension Column | Broadcloth.dbo.Compliance.OverallRating | numeric(18,0) | numeric(18,0)
DWBroadcloth.dbo.DimCompliance.ConditionCategory | Dimension Column | Broadcloth.dbo.ConditionCategory.ConditionCategory | nvarchar(50) | nvarchar(50)
DWBroadcloth.dbo.DimCompliance.WorkerComments | Dimension Column | Broadcloth.dbo.WorkerCheck.WorkerComments | nvarchar(1023) | nvarchar(1023)
DWBroadcloth.dbo.DimCompliance.WorkerHealth | Dimension Column | Broadcloth.dbo.WorkerCheck.WorkerHealth | nvarchar(1023) | nvarchar(1023)
DWBroadcloth.dbo.DimCompliance.Age | Dimension Column | Broadcloth.dbo.WorkerCheck.Age | numeric(18,0) | numeric(18,0)
DWBroadcloth.dbo.DimCompliance.ConditionComments | Dimension Column | Broadcloth.dbo.WorkingConditions.ConditionComments | nvarchar(1023) | nvarchar(1023)
DwBroadcloth.dbo.DimCompliance.AgeDocuments | DimensionColumn | Broadcloth.dbo.WorkerCheck.AgeDocuments | nvarchar(150) | nvarchar(150)
DWBroadcloth.dbo.Customer | Dimesion Table | Broadcloth.dbo.Customer | Table | Table
DWBroadcloth.dbo.Customer.CustomerID | Dimension Key Column | Generated | na | int
DWBroadcloth.dbo.Customer.BaseCurrency | Dimension Column | Broadcloth.dbo.Customer.BaseCurrency | nvarchar(20) | nvarchar(20)
DWBroadcloth.dbo.Customer.BillPostalCode | Dimension Column | Broadcloth.dbo.CustomerOrder.BillPostalCode | nvarcar(12) | nvarcar(12)
DWBroadcloth.dbo.Customer.OrderDate | Dimension Column | Broadcloth.dbo.CustomerOrder.OrderDate | datetime | datetime
DWBroadcloth.dbo.Customer.BillState | Dimension Column | Broadcloth.dbo.CustomerOrder.BillState | nvarchar(20) | nvarchar(20)
DWBroadcloth.dbo.Customer.BillNation | Dimension Column | Broadcloth.dbo.CustomerOrder.BillNation | nvarchar(50) | nvarchar(50)
DWBroadcloth.dbo.Customer.PriceAdjustment | Dimension Column | Broadcloth.dbo.CustomerOrder.PriceAdjustment | numeric(38,4) | numeric(38,4)
DWBroadcloth.dbo.DimDates | Dimesion Table | na | na | Table
DWBroadcloth.dbo.DimDates.Date | Dimension Column | na | na | datetime
DWBroadcloth.dbo.DimDates.Month | Dimension Column | na | na | int
DWBroadcloth.dbo.DimDates.MonthName | Dimension Column | na | na | nvarchar(50)
DWBroadcloth.dbo.DimDates.Quarter | Dimension Column | na | na | int
DWBroadcloth.dbo.DimDates.QuarterName | Dimension Column | na | na | nvarchar(50)
DWBroadcloth.dbo.DimDates.Year | Dimension Column | na | na | int
DWBroadcloth.dbo.DimDates.YearName | Dimension Column | na | na | nvarchar(50)
DWBroadcloth.dbo.DimDates.DayOfWeek | Dimension Column | na | na | int
DWBroadcloth.dbo.DimDates.DayOfMonth | Dimension Column | na | na | int
DWBroadcloth.dbo.DimDates.DayOfYear | Dimension Column | na | na | int
DWBroadcloth.dbo.DimDates.Season | Dimension Column | na | na | nvarchar(50)
Object Name | Description | Source | Source Type | Destination Type

## Roles
Role | Team Member
Project Manager | Bob Smith
Documentation Developer | Bob Smith
Data Warehouse Developer | Sue Jones
ETL developer | Sue Jones
Cube Developer | Sue Jones
Report Developer | Sue Jones
Testers | Tim Thomas
Release Manager | Tim Thomas

## Solution Schedule
BI Solution Projects | Est Hours | Mon | Tue | Wed | Thur | Fri | Mon | Tue | Wed | Thur | Fri
Interview and Identify: | 28 | Mon: ***************************************
Planning and Documenting: | 18 | Thur: **************************
Create the Data Warehouse | 3 | Mon: ****
Extract, Transform, and Load: | 6 | Mon: **********
Create Cubes: | 6 | Mon: ********
Create Reports: | 6 | Mon: ********
Test the Solution: | 21 | Mon: **; Tue: *************************
Approve, Release, and Prepare for next version: | 9 | Thur: *****************

## Estimated Hours
BI Solution Projects | Task | Action Item | Estimated Hours | Actual Hours
Interview and Identify: | Interviews | Talk To Business Owner | 3
|  | Talk to Mangers | 3
|  | Talk to Users | 3
|  | Talk to DBA | 3
| Document Requirements | Create an informal overview | 3
|  | Create a BI solution worksheet | 3
| Locate Data | Review database tables | 3
|  | Review invoice documents | 3
|  | Review sales awards program | 3
| Discuss Feasibility | Decide if the solution will work | 1
28
Planning and Documenting: | Define Team Roles | What role fit this solution? | 1
| Define Team Members | Who will fill each role? | 1
| Define Team Schedule | When will we need them? | 1
| Discuss Feasibility | Decide if the solution will work | 1
| Define IT requirements | Decide which Server will we use for DW, SSIS, SSAS, SSRS | 1
|  | Verify a time slot of Solution automation jobs | 1
| Define Security requirements | Decide which groups will have access to what? | 1
| Define Licensing requirements | Verify that the company has sufficient licensing | 3
| Estimate the cost | Hours * Wages + and additional 10% for unknowns | 1
| Discuss Feasibility | Decide if the solution will work | 1
| Create formal documents | Complete BI solution worksheet | 3
|  | Create a Development Document | 3
18
Create the Data Warehouse | Create the Database | Create the Tables | 2
|  | Define Constraints | 1
3
Extract, Transform, and Load: | Create ETL Code | Create a SQL Script with ETL code | 3
|  | Create a an SSIS package with ETL code | 3
6
Create Cubes: | Create SSAS Database | Create Dimensions | 3
|  | Create Cubes | 3
6
Create Reports: | Create Prototype Reports | Create SSRS Reports | 3
|  | Create Excel Reports | 3
6
Test the Solution: | Requirements | Verify naming | 3
|  | Verify data domains | 3
|  | Verify formula results | 3
|  | Verify presentation formatting | 3
| Performance | Test SSIS ETL performance | 3
|  | Test SSAS Processing performance | 3
|  | Test SSRS Report performance | 3
21
Approve, Release, and Prepare for next version: | Finalize formal documents | Finish development document | 3
|  | Create a formal overview document | 3
|  | Create a lessons learned document | 3
9
|  | TOTAL | 106.7

## ETL Objects
SSIS ETL Objects Worksheet
Object Name | Type | Description | Source | Destination

## Cubes and Dimensions
SSAS Objects Worksheet
Object Name | Description